## Sheet1
Socio Planet' Project - Android & Web
Weekly Targeted Plan (28th August 2017 to 1st September 2017)
Tasks List | Developer Status
Client Feedback ---- >>> 7th & 8th Milestones Feedback - tested in OS 6 & OS 7 versions (Samsung & Xolo devices)
1. Mute from the friends list - nothing happens | Not Done - working to make both friends & chat block as same
2. Block not working from the friends list - it is moving but not showing in the block - from xolo device (os 6) | Not Done - working to make both friends & chat mute as same
3. Other user profile - block not working from xolo device (os 6) | Done
4. Cleared cache from the device, now sent a new message but the older message is getting retrieved. | Done
5. Delivery Status - It should show double tick mark in grey when it is delivered. | Done
6. Chat - Old date, it shows as 1st January, 1970 (screenshot provided) - this is when the scheduled message received. | Done
7. Last seen not working according to the user setting preferences. | Done
8. Scheduled Messages - after creation, it shows duplicates of the created messages in the list from side menu. Secondly show time (hrs & min) in double digits - ex; 01:05. Third point; add text at the time area; 'Scheduled On' | Done
9. Overall point - Things should go work real time, example; when scheduled message was delivered, it is not clearing off from the screen. Like the way, it should work everything (chat, posts) real time without refreshing | Done
10. Scheduled Message - sent user can't see the message in the chat screen (its came but after 2mins not immediately even we refresh), also it shows the notification to the sender even | Done
11. Files open - open in the related format, if the format not there then open in a browser view. Don't open default to browser (ref Whatsapp & IMO) | Done
12. Files upload - when the file format not supports, show the error message but don't show a blank update in the chat | Done
13. Images - even the image was straight it shows in rotated view | Done
14. Chat notifications issue - sometimes it is coming, sometimes not coming. Mostly observed in Xolo device. | It depends on the device and network. It works on all our devices
15. Image - when it shows in a full view, it is little cut off | Done
16. File - Download - After downloading, it is not showing downloaded folder message. When click on that, it should open to the concern format, if the format not available then redirect to browser (just like posts) | Done
17. Videos - it is not playing for the sender, and also not visible to the receiver & not playing | Done
18. Mute & Block - Should be same for chat & friends. Both the functionalities should be same for the entire friend block & mute | Not Done - Working
19. Socio Planet - it shows two folders in the internal memory, why creating two folders. Keep one and don't show sub folders. | Done
20. Posts - Downloaded files shows with different names in the notification and in the folder. Show the same. It is saving as '.post', it should save as .jpg or with that format. | Done
21. Free Style - images shows as little cut off, not complete image. 'x' mark should be purple & white color combination. indicate the rotation with arrow and keep rotation with it. | Done
22. Grid Style - It should have vertical movement also. (Explain)*** | Done
23. Chat screen - should have the redirection to the other user profile when clicks on the name & image | Done
24. Admin Notifications - Time stamp shows wrong. Show app logo under the notifications screen. | Done
25. Notifications - Order of the notifications should be corrected. Latest should be top. | Done
26. Contact join notification - no user image, username is wrong (screenshot provided) | Not Done - Working
27. Chat notifications - should show user profile image | Not Done - Working
Pending Things from last release:
1. Chat Messages to Unknown Users | Done
2. Web Synchronization for Chat | Done
3. Audio selection - Multiple******** | It is not possible for Audio Files
4. Emojis - Shows different | Not Done - Working
Textual changes (minor):
1. Under Settings - Notifications - 'Friends Profile Update' should be changed 'Friends Profile Picture Updates' | Done
2. OTP verification - instead of 'Detecting OTP, please wait...', show message 'OTP not detected on this device. Press back button to enter the OTP manually' | Done
--- Group Chat Functionality
---------- Create New Group (for Admin) UI | Done
---------- Create New Group (for Admin) Functionality | Done
--------- Edit Group (for Admin) UI | Done
--------- Edit Group (for Admin) Functionality | Done
--------- View Group UI and options creations | Done
--------- View Group and its options functionality | Done
-------- User Group UI | Done
-------- User Group functionality | Done
------- Chat Room UI Creation | Done
--------- Group Chat creation | Done
--------- Attachments integration UI + functionality + include all sub dialogs also | Done
--------- More Options integration | Done
--------- Exit Group (for Admin) | Done
---------- Leave Group (for User) | Done
---------- Remove Participant (for Admin) | Done
---------- Make Group Admin (for Admin) | Done
---------- Request to Join Group (for Users who left) | Done
---------- Accept/ Decline Join Request (for Admin) | Done
Notifications for all type of Chats (individual/ scheduled/ group) & Group Chat Requests | Done
Website - Chatting Functionality
--- Chat list screen UI + Functionality (display of Chats & Friends List) | Done
--- Friends List display UI + Functionality (from all the main screens of website) | Done
--- Compose Chat UI + Functionality | Done
--- Text Chatting Functionality | Done
----- Attachments UI + Functionality | Done
------------- Gallery Upload for Photo | Done
------------- Gallery Upload for Video | Done
------------- Gallery Upload for Audio | Done
------------- File Upload (.doc, .xls, .ppt, .pdf, .jpg, .png, .gif, .mp3, .mp4, .zip) | Done
-------- Delete Chat | Done
------- Chat Delivered status (tick marks) display with time schedule | Done
------- Show Typing Status (on Individual Chat & Chat List screens) | Done
--- App Synchronization for Chatting | Done